## Slide 1
PROJECT RAKSHAK
HIT & RUN COMPENSATION
CIVIC & GOVTECH · SATARK
CAMPAIGN & ENABLERS
BETS · SSI + GIG RIDER
ANNUAL OPERATING PLAN · JULY 2026 - JUNE 2027
From programmes
to institutions.
Year 2 runs three core programmes and one civic-tech vertical, deep not wide.
Everything else is an exploratory bet that must earn its way to scale.
Vision Zero Trust · Internal Planning Document

## Slide 2
YEAR 1 IN REVIEW
What one year of audit-led work
put on the board.
Cohort 1 proved the model: youth-generated audits can reach district officials and trigger engineering action.
31
Priority sites audited
18
Cities engaged
25+
Approvals & actions initiated
7+
Engineering works begun
900+
Stakeholder surveys
120+
Victims & families surveyed
30+
Expert consultations
1M+
Citizens reached
150+ members · 50+ experts · AASHA chatbot live · MoUs with Gurugram & Jaipur Traffic Police · DRSC integration begun in SW Delhi
CRASHFREE INDIA · AOP 2026-27
02 / 13

## Slide 3
LEARNINGS FROM YEAR 1
Five lessons that rewired
the Year 2 plan.
Credibility is the currency
Energy and field discovery were strong; report quality must meet DRSC and NHAI standards without rework.
IN Y2
Expert Consortium, certified RSAs, Rakshak Audit Manual v1.0
Awareness alone doesn't move claims
Institutional incapacity and process non-compliance - not just awareness gaps - drive claim dropout.
IN Y2
Shift from awareness drives to stage-wise scheme audit
Depth beats breadth
Parallel full-scale sites diluted bandwidth and institutional trust took longer than planned.
IN Y2
Anchor districts + model-district approach; MACT reform deprioritised
Audits die at submission
Most audit programmes stop at report submission; follow-through is where impact happens.
IN Y2
Public accountability loop - every recommendation tracked to implementation
Plan with rigour
Prior plans carried loosely-scoped activities and untracked workstreams.
IN Y2
Unit-based planning, quarterly phasing, formula-driven rollups
CRASHFREE INDIA · AOP 2026-27
03 / 13

## Slide 4
OBJECTIVES · THE DESTINATION
What must be true
when Year 2 ends.
POSITION By June 2027, CFI is India's audit-and-accountability institution for road safety - the organisation governments call to find where systems break, and to hold the fix to completion.
Rakshak runs inside institutions
An audit pipeline owned by universities, NGO partners and certified RSAs - consortium, Audit Manual v1.0 and a public dashboard - that no longer needs CFI to push every audit.
Y3: national scale through chapters
Compensation fixed, then replicated
Two districts where the hit & run claim pipeline demonstrably works, pilots running beyond them, and the process mapped in 8+ districts - a replication playbook, not a project.
Y3: state-level adoption
SATARK as public infrastructure
Enforcement intelligence live in 30 cities, plus an active exploration track for new govtech products and digital public goods with government partners.
Y3: the road-safety data layer for government
A public evidence brand
Four open data products cited by committees and press, 1M+ citizens engaged through the campaign, and both bets resolved with board-ready designs.
Y3: evidence citations drive inbound demand
CRASHFREE INDIA · AOP 2026-27
04 / 13

## Slide 5
YEAR 2 STRATEGY
One operating model,
run deeper.
01 · AUDIT
Diagnose where systems break - blackspots, claim pipelines, school zones, platform practices - with evidence that survives institutional review.
02 · ADVOCATE
Turn evidence into stakeholder action: DRSC integration, co-designed fixes, model districts, a sustained publishing cadence.
03 · HOLD ACCOUNTABLE
Track every recommendation publicly from submission to implementation; escalate from district fixes to system reform.
THE YEAR 2 SHIFT
From programmes
to institutions.
Expert Consortium + Audit Manual v1.0 give audits institutional authority
Model districts, not scattered pilots - Gurugram, SW Delhi, anchor cities
Civic tech in government hands: SATARK enforcement + four open data products
Publishing cadence: monthly field notes, quarterly findings, year-end audit reports
CRASHFREE INDIA · AOP 2026-27
05 / 13

## Slide 6
KEY FOCUS AREAS
Three core programmes,
two exploratory bets.
Each core programme has a north-star outcome. Bets are exploratory - they scale only if their pilots earn it.
CORE 01
Project Rakshak
Institutionalise the national audit pipeline: three-track model, Expert Consortium, Audit Manual v1.0.
150+ blackspots audited
CORE 02
Hit & Run Compensation
Fix the claim pipeline in two districts, pilot the playbook beyond them, and map the process in 8+ districts.
2 fixed · 8+ mapped
CORE 03
Civic & GovTech
Scale SATARK - the AI enforcement co-pilot for traffic police - to 30 cities; explore the next govtech products and partnerships.
SATARK live in 30 cities
TWO BETS · STAGE-GATED
School Safety Index
The 2,000-school index is parked. First step: validate the IRC:SP:32 rubric on ~100 schools in one city.
Pilot on ~100 schools
Gig Rider Safety
The national study is parked. First step: scoping study + first engagements with delivery platforms.
Scoping + platforms
CRASHFREE INDIA · AOP 2026-27
06 / 13

## Slide 7
DEEP DIVE · CORE 01
Project Rakshak:
put the audit pipeline inside institutions.
THE THREE-TRACK MODEL · RUN BY INSTITUTIONS, NOT BY CFI ALONE
A
Institutional
IIT / NIT / SPA student teams under expert mentors; IRC-aligned rubric
~90 sites
B
NGO Partners
NGO field teams; 100% desk review + 10-15% physical re-checks by CFI
~20 sites
C
Certified RSAs
CRRI-certified auditors; full IRC SP:88 - usable by NHAI without rework
~40 sites
Anchor districts: Gurugram (NH-48) · SW Delhi (NH-48/44) · Jaipur (NH-8) · +10 exploratory cities
crashfreeindia.org/rakshak/dashboard
Public accountability dashboard - the institutional spine
Every site tracked in public: identification > audit > authority review > engineering implementation. [Insert live dashboard screenshot before circulation]
FY 2026-27 TARGETS
150+
blackspots audited
100+
recommendations accepted
75+
implementations initiated
12+
DRSC presentations
v1.0
Rakshak Audit Manual + 4 Expert Consortium meetings
CRASHFREE INDIA · AOP 2026-27
07 / 13

## Slide 8
DEEP DIVE · CORE 02
Hit & Run Compensation:
fix two districts, map eight.
FOUR PILLARS · AUDIT-LED, RESEARCH-EMBEDDED
Scheme audit & process documentation
Stage-wise pipeline audit in Gurugram: FIR to GI Council disbursal; 20-30 claims tracked end-to-end.
Institutional capacity building
Fellow-in-Residence at Tehsildar office; SOP reference cards; training-gap assessment - research-embedded, not social work.
Victim identification & AASHA
DLSA-partnered helpdesks; AASHA QR deployment at police stations and trauma centres; usage measured monthly.
Policy audit & advocacy
'Where the Pipeline Breaks' - comprehensive scheme audit submitted to MoRTH; quarterly findings + public brief.
Fix > pilot > map: FIX Gurugram + SW Delhi (measured uptake lift) · PILOT the playbook in Jaipur + watchlist districts · MAP the claim process in 8+ districts by June 2027
FY 2026-27 TARGETS
2
districts FIXED - measured claim-uptake lift, -20% processing time
2+
districts PILOTING the fixed-pipeline playbook
8+
districts process-MAPPED by June 2027
20-30
claims tracked FIR to disbursal
1
scheme audit report to MoRTH (Apr-May '27)
CRASHFREE INDIA · AOP 2026-27
08 / 13

## Slide 9
DEEP DIVE · CORE 03
Civic & GovTech: take SATARK
from 2 cities to 30.
SATARK · THE ENFORCEMENT CO-PILOT FOR TRAFFIC POLICE
ANPR
plate scan
ULIP
vehicle records
SATARK
rule engine
Billboard +
officer app
Interception
logged
PROVEN IN THE FIELD · CUMULATIVE, LIVE DEPLOYMENTS
3,00,000+
vehicles scanned at live sites
Rs 30 Cr+
pending challan value surfaced
350+
vehicles intercepted in the field
2 cities
live today - Jaipur & Bengaluru
BEYOND SATARK · DATA STACK + GOVTECH EXPLORATION
Sustain the four open data products: Defect Repository (daily, 146 districts) · Parliament tracker (1,423 questions) · SC Litigation Tracker · Crash Data Dashboard (CC-BY).
Scout the next govtech wedges: new digital public goods, state integrations, and partnerships across the ULIP / MoRTH ecosystem.
FY 2026-27 TARGETS
30
cities live with SATARK - Gurugram, Pune & Ahmedabad first
1,000+
field interceptions logged - a floor, not a ceiling
4
open data products sustained & cited in DRSCs and press
2+
new govtech / DPG opportunities scoped with partners
CRASHFREE INDIA · AOP 2026-27
09 / 13

## Slide 10
THE BETS
Two bets, exploratory now -
scaled only if they earn it.
School Safety and Gig Rider stay exploratory this year. Each runs a small pilot, released against a board-approved design.
BET 01 · STAGE-GATED
School Safety Index
The 2,000-school index is parked, not killed.
THE PILOT
Validate the IRC:SP:32-2023 rubric (44 checks, 13 sections) on ~100 school zones in one anchor city; test the Zone Captain audit model end-to-end.
THE GATE
A defensible per-school method and validated rubric > board approves a multi-city index in Year 3.
BET 02 · STAGE-GATED
Gig Rider Safety
The national study is parked until the field model is proven.
THE PILOT
Scoping study on gig rider crash data + first structured engagements with delivery platforms and OMI Foundation.
THE GATE
3+ platforms at the table and a viable study design > board approves the full programme in Year 3.
Both bets are stage-gated · nothing scales without a board-approved design · a proven bet returns as a Year 3 programme
CRASHFREE INDIA · AOP 2026-27
10 / 13

## Slide 11
OBJECTIVES & KPIS
One north star per programme,
measured quarterly.
Project Rakshak
NORTH STAR
75+ implementations initiated
SUPPORTING
150+ audits · 100+ recommendations accepted · 12+ DRSC presentations · Audit Manual v1.0
Hit & Run Compensation
NORTH STAR
2 districts fixed, 8+ mapped
SUPPORTING
-20% median processing time · 20-30 claims tracked · pilots beyond model districts · audit report to MoRTH
Civic & GovTech
NORTH STAR
SATARK live in 30 cities
SUPPORTING
1,000+ interceptions logged · 4 open data products cited in DRSCs & press · 2+ new govtech opportunities scoped
Bets (SSI + Gig Rider)
NORTH STAR
2 board-ready pilot designs
SUPPORTING
SSI rubric validated on ~100 schools · gig scoping study · 3+ platform engagements · scaled only on board approval
Campaign & Comms
NORTH STAR
1M+ engaged via 'Safety is the New Swag'
SUPPORTING
50 micro-influencers · OOH in 3-4 cities · monthly field notes · quarterly findings · year-end reports
CRASHFREE INDIA · AOP 2026-27
11 / 13

## Slide 12
ENABLERS
The campaign and the backbone
behind the plan.
SAFETY IS THE NEW SWAG · THE CAMPAIGN
Media advocacy
Editorial partnerships, radio & podcast integration, PSA distribution
Digital advocacy
50 micro-influencers, branded short films, #SafeSwag digital IPs
Offline awareness
OOH in 3-4 cities, guerilla installations, event co-branding
Community mobilization
College competitions, app-based engagement, real-life stories
All four campaign pillars are now active workstreams (the prior plan ran only one of four).
ORG BACKBONE
Core team salaries & benefits
IRSC institutional support & expert consultation
IT, SaaS & AI tooling (Workspace, Slack, Claude)
M&E, statutory & impact audit
Travel, branding, compliance
CRASHFREE INDIA · AOP 2026-27
12 / 13

## Slide 13
WHAT SUCCESS LOOKS LIKE · JUNE 2027
Systems work because
we hold them accountable.
Rakshak running inside institutions: consortium, Audit Manual v1.0, and a public dashboard tracking 75+ implementations
Claim pipeline fixed in two districts, piloted beyond them, and mapped in 8+ - a replication playbook, not a project
SATARK live in 30 cities, 1,000+ interceptions logged, and a govtech pipeline positioning CFI as government's road-safety data layer
Two board-ready pilot designs that decide whether School Safety and Gig Rider become full Year 3 programmes
An Expert Consortium, an Audit Manual, and a publishing cadence that outlive any single cohort
CRASHFREE INDIA · AOP 2026-27 · INTERNAL PLANNING DOCUMENT